## Test Plan
Test Plan
1. Test Plan ID: | PriyoShop-001
2.Introduction: | It is System Test Plan for Online Shopping System. PriyoShop is a web application,provides access to new user create an account in the website.User purchases any products in the online system then choice of products add to cart then bill pay by bkash, by nagad,by visa etc.
3.Test Items: | Testing should be done on both Front end and Back end of the application on the Windows.User interface: Personal information, just like User name,email,mobile number,address,date of birth etc
4.References: | Test Plan,Test Strategy, Project Plan, Project Guidelines, SRS(System Requirement Specification), Use Case Documents,High Level Design docs, Low Level Design docs, Process guide line docs, prototypes.
5.Features To Be Tested: | The features which are to be tested are Login Page,Registration Page,Log Out Page etc
6.Feature Not To Be Tested: | The features which are not to be Tested Payment Using Paypal Features is above to remove from the application.There is no need to test this feature
7.Test Approach: | We follow SDLC in this project.
8.Entry Criteria: | Verify if the test environment is available and ready for use. Verify test tools installed in the environment are ready for use.a) Test design -Team information, responsibilities,schedule, requirements, Test cases template etc Verify if test data is available and validated for correctness of data
9.Exit Criteria: | Verify if all tests planned have been run.Verify if all high risk areas are completely tested.All possible test cases executed maximum defects fixed , final regression performed successfully, confidence on test process, time limitations, budget limitations
10.Suspension Criteria: | If any of the major functionalities are not functional or system experiences login issues then testing should suspend
11.Roles & Responsibilities: | Test plan should be prepared by Test Lead Preparation and Execution of tests should be carried out by testers.
12. Schedule: | Perform test execution,Test Reporting,Bug Reporting,Mind-map etc
13.Training: | Training Program on Manual Testing and API Testing Use Postman,Test automation training using Selenium Tool
14. Test Environment | Hardware,Software and any other tools that are needed for a test environment. Application Type: Web Application, Internet and Public. Server Side: Windows Server, Web Server,Data Storage Tools Client Side: Windows 11,XLS Sheet,Xmind Etc
15.Test Deliverables: | List of documents need to be delivered at each phases of testing life cycle. The list of all test artifacts is Test Cases and Bug Report,Test Plan,Review Reports,RTM Test Scenario docs,Defects Report,Test Summary Report etc
16.Approvals: | Tasks Author/Role Date & Signature 1)Test Plan Documentation Ehsan (Test Lead) 2)Review SomeName(QA Analist) 3) Approval SomeName(Project Manager)
17.Glossary: | AUT-Application Under Test…PIN-Project Initiation Note….SRS-Software Requirement Specification..

## Test Case Priyoshop Web
Product Name | Priyoshop | TC Start Date | 10/28/2022 | TC Execution Start Date | 10/28/2022 |  |  |  | Test Case Summary
Module Name | User Account | TC End Date | 10/28/2022 | Tc Execution End Date | 10/28/2022 |  |  |  | Pass | 39
Developer Name | Mr. Y | Test Case Developed By | Aysha Shila | Browser(tested) | Chrome |  |  |  | Fail | 13
TC Executed By | Aysha Shila | Test Case Reviewed By | N/A | Performance(tested) | No |  |  |  | Warning | 0
[9 empty] | Not Executed | 0
[9 empty] | Out Of Scope | 0
[9 empty] | Total | 52
Test Case ID | Feature | Test Scenario | Test Type | Test Steps | Test Data | Precondition | Postcondition | Expected Results | Actual Results | Status | Bug Screenshot | Dev Comment(if any) | Remarks
TC_001 | Sign UP Field | Create a valid email id & valid Password | Fuctional Testing | 1.Open browser 2.go to the URL 3.click on sign 4.fill up all field correctly 5.type email id & password Field correctly 6.click on register button | https://www.priyoshop.com shila@gmail.com password:1234@abcd | Valid URL Test Data | User should able to see the home page | Successful login | Valid email Id & valid password | Pass |  | N/A
TC_002 | Sign UP Field | Create a invalid email id & valid Password | Fuctional Testing | 1.Open browser 2.go to the URL 3.click on sign 4.fill up all field correctly without email field 5.type email id incorrect and password field correct 6.click on register button | https://www.priyoshop.com shila12@ab@gmail.com password:1234@abcd | Valid URL Test Data | User should able to see the home page | Should not give error or popup message | InValid Email id & valid Password | Fail | Invalid email Id | N/A
TC003 | Sign UP Field | Create a valid email id & invalid Password | Fuctional Testing | 1.Open a browser 2.go to the URL 3.click on sign 4.fill up all field correctly without password field 5. click on register button | password:123456 www.priyoshop.com | Valid URL Test Data | User should not able to see the home page | should give a error or pop message | Valid Email id & invalid Password | Fail | Invalid password | N/A
TC004 | Sign UP Field | Create a valid email Id &password Invalid phone no | Fuctional Testing | 1.Open a browser 2.go to the URL 3.click on sign 4.fill up all field correctly without phone no field 5. click on register button | phone no:01645367401 https://www.priyoshop.com | Valid URL Test Data | User should not able to see the home page | should give a error or pop message | Valid Email id & valid Password Invalid phone no | Fail |  | N/A
TC005 | Sign UP Field | Create a valid email id valid password and valid phone no | Fuctional Testing | 1.Open a browser 2.go to the URL 3.Click on Sign 4.fill up all field correctly 5.click on registration button | email:shila@gmail.com password: abcd@1234 phone no:01675453610 | Valid URL Test Data | User should able to see the home page | Successful login | Valid email id & password valid phone no | Pass |  | N/A
TC006 | Sign UP Field | Create a email id Field null value and valid password and valid phone num | Fuctional Testing | 1.Open a browser 2.go to the url 3.Click on sign 4.fill up all field correctly without email field 5.Email field use null value 6.click on registration button | email:null value password: abcd@1234 phone no:01675453610 | Valid URL Test Data | User should not able to see the home page | should give a error or pop message | Valid password and valid phone no email id field null value | Fail | Email id null value | N/A
TC007 | Sign UP Field | Create a valid email id and valid phone no but null value password | Fuctional Testing | 1.Open a browser 2.go to Url 3.click on sign 4.fill up all field correctly without password field 5.password field use null value 6.click on registration button | email:shila@gmail.com password: null value phone no:01675453610 | Valid URL Test Data | User should not able to see the home page | should give a error or pop message | Valid email id valid phone no null value password field | Fail | null value password | N/A
TC008 | Registration Field | Create a valid phone num and email & password field null | Fuctional Testing | 1.Open a browser 2.go to Url 3.click on sign 4.fill up all field correctly without password field & email field 5.Email&password field use null value 6.click on registration button | email:null value password: null value phone no:01675453610 | Valid URL Test Data | User should not able to see the home page | should give a error or pop message | Valid phone no and email & password field null value | Fail | password field null value | N/A
TC009 | Sign UP Field | Create a valid email & valid phone no but password & confirm password don't match | Fuctional Testing | 1.Open a browser 2.go to URL 3.click on sign 4.fill up all field correctly without password & confirm password field 5.password field & confirm password field value different 6.click on registration button | email:shila@gmail.com phone no:01675453610 password:abcd@1234 confirm password:1234@abcd | Valid URL Test Data | User should not able to see the home page | should give a error or pop message | Valid email id & valid phone no but password and confirm password different value | Fail | password & confirm password diffrent value | N/A
TC010 | Sign UP Field | Create a valid email Id valid password and valid phone no but user name different | Fuctional Testing | 1.Open a browser 2.go to URL 3.click on sign 4.fill up all field correctly without user name field 5.click on registration button | user name: shila islam email:shila@gmail.com phone no:01675453610 password:abcd@1234 | Valid URL Test Data | User should not able to see the home page | should give a error or pop message | Valid Email id & valid Password valid phone no user name different | Fail |  | N/A
TC011 | Log in Field | Valid user name & invalid password | Fuctional Testing | 1.Open a browser 2.go to the url 3.Click on sign 4.fill up all field correctly without password field 5.click on log in button | user name: shila@gmail.com password:abcd@1234 | Valid URL Test Data | User should not able to see the home page | should give a error or pop message | Valid user name invalid password | Fail | invalid password | N/A
TC012 | Sign in Field | Valid user name & valid password | Fuctional Testing | 1.Open a browser 2.go to URL 3.click on sign 4.fill up all field correctly 5.click on log in button | User name:shila@gmail.com Password:1234@abcd | Valid URL Test Data | User should able to see thr home page | Successful login | Valid user name valid password | Pass |  | N/A
TC013 | Sign in Field | Invalid user name & valid password | Fuctional Testing | 1.Open a browser 2.go to URL 3.click on sign 4.fill up all field correctly without user field 5.click on log in button | User name :aysha@gmail.com Password : 1234@abcd | Valid URL Test Data | User should not able to see the home page | should give a error or pop message | Invalid user name valid password | Fail | Invalid user name | N/A
TC014 | Sign in Field | Verify forgot password | Fuctional Testing | 1.Open a browser 2.go to URL 3.click on sign 4.fill up all field correctly without password field 5. verifying forgot password 6.click on login button | Verify password | Valid URL Test Data | User should able to see home page | Successful login | Verifying password field | Pass |  | N/A
TC015 | Sign in Field | Verify email ID field | Fuctional Testing | 1.Open a browser 2.go to Url 3.click on sign 4.fill up all field correctly without email field 5.verify email field 6.click on login button | Verify email | Valid URL Test Data | User should able to see home page | Successful login | Verifying email field | Pass |  | N/A
TC016 | Sign in Field | Keeping mandatory Fields Blank | Fuctional Testing | 1.Open a browser 2.go to URL 3.click on sign 4.mandatory fields blank 5.click on log in button |  | Valid URL Test Data | User should not able to see home page | Should give error or popup message | Not found as per expectation | Fail | Mandatory field blank | N/A
TC017 | Sign in Field | Checking alert message for all mandatory fields | Fuctional Testing | 1.Open a browser 2.go to URL 3.click on sign | N/A | Valid URL Test Data | User should not able to see home page | Should give error or popup message | Not found as per expectation | Pass |  | N/A
TC018 | Sign in Field | User name use special character | Fuctional Testing | 1.Open a browser 2.go to URL 3.click on sign 4.user name use special character 5.click on login button | Aysha@&shila | Valid URL Test Data | User should not able to see home page | Should give error or popup message | Not found as per expectation | Fail | User name field use special character | N/A
TC019 | Sign in Field | Validating an email id can only be used one time | Fuctional Testing | 1.Open a browser 2.go to URL 3.click on sign 4.valid email id can only be used one time 5.click on login button | shila@gmail.com | Valid URL Test Data | User should able to see home page | Successful login | valid email id one time used | Pass |  | N/A
TC020 | Sign in Field | Valid phone no can be used one time | Fuctional Testing | 1.Open a browser 2.go to URL 3.click on sign 4. valid phone no used one time 5.click on login button | 1675864510 | Valid URL Test Data | User should able to see home page | Successful login | valid phone no use one time | Pass |  | N/A
TC021 | Sign in Field | Checking login wrong credentials in email and password field | Fuctional Testing | 1.Open a browser 2.go to URL 3.click on sign 4.worng credential in email & pasword field 5.click on log in button | abcdrt@&.gmail.com.ukij | Valid URL Test Data | User should not able to see home page | Should not allow user to login and display an error messeage | Not found as per expectation | Pass |  | N/A
TC022 | Sign in Field | Checking login valid credentials in email and password field | Fuctional Testing | 1.Open a browser 2.go to URL 3.click on sign 4.valid email & valid password 5.click on login button | shila@gmail.com | Valid URL Test Data | User should able to see home page | Successful login | valid email and valid password | Pass |  | N/A
TC023 | Sign in Field | Checking by selecting ‘Forgot Password’ multiple times | Fuctional Testing | 1.Open a browser 2. go to URL 3.click on sign 4.forgot password use multiple times 5.click on login button | N/A | Valid URL Test Data | User should not able to see home page | Account should be temporarily restricted and a message should be displayed | Found as per expectation with a message | Pass |  | N/A
TC024 | Sign in Field | Inputing weak password length | Fuctional Testing | 1.Open a browser 2.go to URL 3.click on sign 4.input weak password in password field 5.click on login button | 123456 | Valid URL Test Data | User should allow to register | Successful login | Found as per expectation with a message | Pass |  | N/A
TC025 | Sign in Field | Checking confirmation mail sent to the registered email | Fuctional Testing | 1.Open a browser 2.go to URL 3.click on sign 4.fill up all field correctly 5.click on login in button | User name:Aysha Shila email:shila@gmail.com phone no:01675453610 password:1234@&abcd | Valid URL Test Data | User should allow to register | Successful login | Found as per expectation with a message | Pass |  | N/A
TC026 | Sign in Field | Checking 'Sign in with Facebook' | Fuctional Testing | 1.Open a browser 2.go to Url 3.click on sign in register button 4.sign in with facebook | Click on sign in with facebook account | Valid URL Test Data | User should allow to register | Successful login | Found as per expectation with a message | Pass |  | N/A
TC027 | Sign in Field | Checking 'Sign in with Google' | Fuctional Testing | 1.Open a browser 2.go to Url 3.click on sign in register 4.Sign in with google | Click on sign in with Google | Valid URL Test Data | User should allow to register | Successful login | Found as per expectation with a message | Pass |  | N/A
TC028 | Register Field | Checking spelling or grammatical mistakes | UI Testing | 1.Open a browser 2. Go to the URL www.priyoshop.com/ 3.Click on register button | N/A |  | User should allow to register | No spelling or grammatical mistakes | Found as per user expectation | Pass |  | N/A
TC029 | Register Field | Verifying the font, text color and style | UI Testing | 1.Open a browser 2. Go to the URL www.priyoshop.com/ 3.Click on register button | N/A | N/A | User should allow to register | Should be as per the recuirement | Found as per user expectation | Pass |  | N/A
TC030 | Register Field | Verifying mandatory field is marked with a red asterisk | UI Testing | 1.Open a browser 2. Go to the URL www.priyoshop.com/ 3.verify mandatory field correctly 4.Click on register button | N/A | N/A | User should allow to register | Should be as per the recuirement | Found as per user expectation | Pass |  | N/A
TC031 | Sign UP Field | Checking alignment of the fields | UI Testing | 1.Open a browser 2.Go to the URL www.priyoshop.com/ 3.click on register button | N/A | N/A | User should allow to register | Proper alignment of the fields should be present | Found as per user expectation | Pass |  | N/A
TC032 | Register Field | Checkbox beside 'Sign Up for Newsletter' | UI Testing | 1.Open a browser 2.Go to the URL www.priyoshop.com 3.click on register button | N/A | N/A | User should allow to register | Checkbox should be present | Found as per user expectation | Pass |  | N/A
TC033 | Register Field | Checkbox beside 'Sign Up for Newsletter' | UI Testing | 1.Open a browser 2. Go to the URL www.priyoshop.com 3.click on register button | N/A | N/A | User should allow to register | Checkbox should be present | Found as per user expectation | Pass |  | N/A
TC034 | Register Field | Checkbox I accept privacy policy | UI Testing | 1.Open a browser 2. Go to the URL www.priyoshop.com 3.click on I accept privacy policy button | N/A | N/A | User should allow to register | Checkbox should be present | Found as per user expectation | Pass |  | N/A
TC035 | Register Field | Fill Up address field data correctly | Functional Testing | 1.Open a browser 2. Go to the URL www.priyoshop.com 3.Fill up address field data properly 4..click on register button | Street address:20/3 west tejturi bazar ,dhaka-1215 Country:Bangladesh District:Dhaka Police Station:Tegjoan | N/A | User should allow to register | Address field fill up properly | Found as per user expectation | Pass |  | N/A
TC036 | Register Field | Fill Up address field data incorrectly | Functional Testing | 1.Open a browser 2. Go to the URL www.priyoshop.com 3.Fill up address field data incorectly 4.Click on register button | Street address:west tejturi bazar ,dhaka-1215 Country:Bangladesh District:Khulna Police Station:Kafrul | Valid URL Test Data | User should not allow to register | Address field fill up incorectly | Not found as per expectation | Fail |  | N/A
TC037 | Register Field | Only one user name enter user field one time | Functional Testing | 1.Open a browser 2.Go to URL www.priyoshop.com 3.User name field enter data one time only 4.Click on register button | User name :Aysha Akter Email:shila@gmail.com phone no:01645367510 | Valid URL Test Data | User should allow to register | Fill up all field correctly | Found as per user expectation | Pass |  | N/A
TC038 | Register Field | User name through Email or Phone no | Functional Testing | 1.Open a browser 2.Go to the URL www.priyoshop.com 3.Fill up user field through email or phone no | User name medium:Email or Phone no | Valid URL Test Data | User should allow to register | Should be as per the recuirement | Found as per user expectation | Pass |  | N/A
TC039 | Register Field | Checking copy paste functionality in every field | Usability Testing | 1.Open a browser 2.Go to the URL www.priyoshop.com 3.Check the copy paste functionality in every field 4.Click on register button | Aysha8888 |  | User should allow to register | Should copy and paste text from fields | Fuctioning Successfully | Pass |  | N/A
TC040 | Register Field | Checking keyboard tab button functionality | Usability Testing | 1.Open a browser 2.Go to the URL www.priyoshop.com 3.Check the keyboard tab button fuctionality 4.Click on register button | Enter tab every field | Valid URL Test Data | User should allow to register | Should switch to another field and highlight text | Fuctioning Successfully | Pass |  | N/A
TC041 | Register Field | Checking keyboard enter button functionality | Usability Testing | 1.Open a browser 2.Go to the URL www.priyoshop.com 3.Check keyboard enter button functionality 4.Click on register button | Input enter in every field | Valid URL Test Data | User should allow to register | Should switch to another field | Fuctioning Successfully | Pass |  | N/A
TC042 | Register Field | Checking Red Star mark button functionality | Usability Testing | 1.Open a browser 2.Go to the URL www.priyoshop.com/ 3.Check red star mark button functionality 4.Click on register button | Input enter value red star mark button | Valid URL Test Data | User should allow to register | Enter value in red star mark button | Fuctioning Successfully | Pass |  | N/A
TC043 | User Field | Add To Cart | Functional Testing | 1.Open a browser 2.Go to the URL www.priyoshop.com/ 3.Choice of products add to cart system | N/A | Valid URL Test Data | N/A | N/A | Fuctioning Successfully | Pass |  | N/A
TC044 | User Field | Search of Products | Functional Testing | 1.Open a Browser 2.Go to URL www.Priyoshop.com 3.User search of products | N/A | Valid URL Test Data | N/A | N/A | Fuctioning Successfully | Pass |  | N/A
TC045 | User Field | Contact with User Email and Phone no | Functional Testing | 1.Open a browser 2.Go to the URL www.priyoshop.com 3.Contact with email and phone no | Email:support@priyoshop.com Phone:09636-102030 | Valid URL Test Data | N/A | N/A | Fuctioning Successfully | Pass |  | N/A
TC046 | User Field | User Communication with facebook,instragram,twitter etc | Functional Testing | 1.Open a browser 2. Go to the URL www.priyoshop.com 3.communication with facebook,instragram,whatsup etc |  | Valid URL Test Data | N/A | N/A | Fuctioning Successfully | Pass |  | N/A
TC047 | User Field | User Security policy | Functional Testing | 1.Open a browser 2. go to the URL www.priyoshop.com 3.user security policy maintain successfully | N/A | Valid URL Test Data | N/A | N/A | Fuctioning Successfully | Pass |  | N/A
TC048 | User Field | Orders,Stock Availability&Pricining | Functional Testing | 1.Open a browser 2.go to the URL www.priyoshop.com 3.orders,stock & pricing successfully | N/A | Valid URL Test Data | N/A | N/A | Fuctioning Successfully | Pass |  | N/A
TC049 | User Field | Shipping & Replacement | Functional Testing | 1.Open a browser 2. go to the URL www.priyoshop.com 3.shipping & replacement successfully | N/A | Valid URL Test Data | N/A | N/A | Fuctioning Successfully | Pass |  | N/A
TC050 | User Field | Privacy Policy | Functional Testing | 1.Open a browser 2.go to the URL www.priyoshop.com 3. privacy policy maintain successfully | N/A | Valid URL Test Data | N/A | N/A | Fuctioning Successfully | Pass |  | N/A
TC051 | User Field | Orders in Products | Functional Testing | 1.Open a browser 2.go to the URL www.priyoshop.com 3.user orders with Valid user name & valid password Successfully 4.Login successfully | User name:Aysha Akter Password:1234@&abcd | Valid URL Test Data | N/A | N/A | Fuctioning Successfully | Pass |  | N/A
TC052 | User Field | Payment System | Functional Testing | 1.Open a browser 2.go to the URL www.priyoshop.com 3. payment policy maintain successfully | By Bkash,By Nagad,Vasa Card etc | Valid URL Test Data | N/A | N/A | Fuctioning Successfully | Pass |  | N/A

## Test case Priyoshop Mobile
Product Name | PriyoShop | TC Start Date | 2022-10-28 | TC Execution Start Date | 2022-10-28 |  |  |  |  | Test Case Summary
Module Name | Registration Field | TC End Date | 2022-10-28 | TC Execution End Date | 2022-10-28 |  |  |  |  | Pass | 2
Developer Name | Mr.X | Test Case Developed By | Aysha Shila | Browser Tested | Chrome |  |  |  |  | Fail | 6
TC Executed By | Aysha Shila | Test Case Review By | N/A | Performance Tested | NO |  |  |  |  | Warning | 0
[10 empty] | Total | 8
Test Case ID | Feature | Test Case Description | Test Type | Test Steps | Test Data | Precondition | Postcondition | Expected Results | Actual Results | Status | Bug Screenshot | Comment(if any)
TC_001 | Email Field | Create a valid user name & valid phone no valid email id | Functional Testing | 1.Open a browser 2.go to URL 3.click on sign 4.fill up all field correctly 5.click on register button | User name:01551234908 email id:fariyasqa@gmail.com phone no:01551234908 | Valid URL test data | User should be able to see home page | Successful Login | valid Email ID valid user name & valid phone no | Pass |  | N/A
TC_002 | Phone no Field | Create a valid user name & Invalid phone no valid email id | Functional Testing | 1.Open a browser 2.go to URL 3.click on sign 4.fill up all field correctly without phone no field 5.click on register button | User name:01551234908 email id:fariyasqa@gmail.com phone no:0155123490811 | Valid URL test data | User should not be able to see home page | should give error message or popup message | invalid phone no | Fail | Invalid phone no | N/A
TC_003 | Email Field | Create a valid user name & valid phone no invalid email ID | Functional Testing | 1.Open a browser 2.go to URL 3.click on sign 4.fill up all field correctly without email field 5.click on register button | User name:01551234908 email id:ayshasqa@gmail.com phone no:01551234908 | Valid URL test data | User should not be able to see home page | should give error message or popup message | Invalid email id | Fail | Invalid Email Id | N/A | 0
TC_004 | User Field | Valid email ID & valid phone no user field use special character | Functional Testing | 1.Open a browser 2.go to URL 3.click on sign 4.fill up all field correctly without user field 5.User field use special character 6.click on register button | User name:0155@&123908 email id:fariyasqa@gmail.com phone no:01551234908 | Valid URL test data | User should not be able to see home page | should give error message or popup message | User field use special character | Fail | user field use special charecter
TC_005 | User Field | Valid email ID & valid phone no invalid user field | Functional Testing | 1.Open a browser 2.go to URL 3.click on sign 4.fill up all field correctly without user field 5.Invalid user field 6.click on registration button | User name:01689012340 email id:fariyasqa@gmail.com phone no:01551234908 | Valid URL test data | User should not be able to see home page | should give error message or popup message | Invalid user field | Fail | Invalid user field | N/A
TC_006 | Phone no Field | Valid email id & valid user name but phone no field use special character | Functional Testing | 1.Open a browser 2.go to URL 3.click on sign 4.fill up all field correctly without phone no field 5.click on register button | User name:01551234908 email id:fariyasqa@gmail.com phone no:01689012340 | Valid URL test data | User should not be able to see home page | should give error message or popup message | Invalid phone no | Fail | Invalid phone no | N/A
TC_007 | Password Field | Password field & confirm password don't match | Functional Testing | 1.Open a browser 2.go to URL 3.Click on Sign 4.password & confirm don' match | password:1234abcd confirm Password:1234@&abcd | Valid URL test data | User should not be able to see home page | should give error message or popup message | Password & confirm don't match | Fail | password don't match | N/A
TC_008 | Password Field | Password field & confirm password match | Functional Testing | 1.Open a browser 2.go to URL 3.click on sign 4.fill up all field correctly 5.password & confirm password match 6.click on registration button | password:1234@&abcd confirm Password:1234@&abcd | Valid URL test data | User should able to see home page | Successful Login | password & confirm match | Pass |  | N/A

## Bug Report
TC ID | Issue Type | Expected Result | Actual Result | Reproducing Steps | Environment | Severity | Screenshots | Responsible QA
TC_001 | Enforcing user to enter optional field | Should not give error or popup message | Invalid email address | 1.go to URL 2.Select register from login button 3.Enter valid data in the madatory field only 4.Click on register button | Production | P1 | Invalid email Id | Aysha Shila
TC_002 | Register With Invalid Email Id | Should not give error or popup message | Invalid email address | 1.go to URL www.priyoshop. com 2.Click on register button with write corner 3.Fill all the field invalid credencials 4.Click 'Create an account' | Production | P1 | Invalid email Id | Aysha Shila
TC_003 | Register With Weak Password | Should not give error or popup message | Weak Password Field | 1.go to URL www.priyoshop.com 2.Select register from login button 3.Enter valid data in the madatory field only 4. Enter weak password in password field 5.Click on register button | Production | p3 | Weak password | Aysha Shila
Aysha Shila

## Test Metrics
Test Metrics
//SL | Metrics | Description | Result(%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (52/52)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/52)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (39/52)*100 = 75
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (13/52)*100 = 25
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/52)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A

## Test Report
Test Case Report
Project Name |  | PriyoShop |  |  |  | Testing Environment |  | Google Chrome Browser
Module Name |  | Sign UP/Register,Sign In
Test Case Version | [5 empty] | Total NO | Status
Written By |  | Aysha Akter |  |  |  | 39 | PASS
Executed By |  | Aysha Akter |  |  |  | 13 | FAIL
Reviewed By |  | Ehsanul Alam Sabbir |  |  |  | 0 | Not Executed
Test Execution Result | [5 empty] | 0 | Out of Scope
Test Case | Pass | Fail | Not Executed | Out Of Scope | Total TC
| 39 | 13 | 0 | 0 | 52
Grand Total | 39 | 13 | 0 | 0 | 52
LIMITATION
Documents |  |  |  | Received | Useful
PRD |  |  |  | NO | NO
User Stories |  |  |  | NO | NO
| Testing Type In Scope | Description
Yes/No. Justification (If No): | Funtional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not .
Yes/No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as integration testing
Yes/No. Justification (If No): | Negative Testing | Testing having the mindset of ''attitude to break'' using incorrect data and invalid inputs
Yes/No. Justification (If No): | Usability Testing | Test application from user friendliness perspective
Yes/No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether eb application runs on all versions of all browsers or not
Yes/No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/No. Justification (If No): | Risk Based Testing or Regression Testing | Risk-Based testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing